## CPM Example
Gantt Chart vs Critical Path — Worked Example
Website migration, 9 activities. Blue cells are inputs; black cells are formulas. pminfohub.org
ID | Activity | Duration (days) | Predecessors | Early start | Early finish | Late start | Late finish | Total float | Critical? | Helper: critical | Helper: float
A | Content audit | 5 | — | 0
B | Information architecture | 4 | A
C | Visual design | 8 | B
D | Content rewrite | 10 | B
E | Front-end build | 9 | C
F | CMS setup & data model | 6 | B
G | Content load | 4 | D, F
H | Integration & QA | 5 | E, G
I | Cutover & DNS switch | 2 | H
Project duration (days)
Critical path
Tasks with float (safe to slip)

## How to use
How this workbook works
1. Change only the blue cells: duration and the predecessor note for each activity.
2. Early start / early finish are the forward pass. Early start = the latest early finish of the predecessors.
3. Late start / late finish are the backward pass, walked back from the project finish date.
4. Total float = late start - early start. Zero float means the activity is on the critical path.
5. Critical activities are shaded and flagged Yes. Crashing or fast tracking anything else buys you no time.
6. Watch near-critical chains: any path with float under 10% of the project duration can become critical.
7. If you add or remove activities, update the early start and late finish formulas so they point at the right predecessor and successor rows.
Free to use and share, including commercially. Attribution appreciated but not required.
Guide: https://pminfohub.org/articles/gantt-chart-vs-critical-path